ONCOBIOLOGICS, INC.

CLINICAL OPERATIONS PLAN

Protocol CERVIMAB-301 — Phase 3

A Phase 3, Randomized, Double-Blind, Placebo-Controlled, Multicenter Study
of Cervimab versus FOLFOX-4 + Bevacizumab in dMMR/MSI-H Metastatic Colorectal Cancer

| Document Number | COP-CERVIMAB-301-001 |
| --- | --- |
| Protocol Number | CERVIMAB-301 v1.0 |
| Indication | dMMR/MSI-H Metastatic Colorectal Cancer (1L) |
| Investigational Product | Cervimab (Anti-PD-1 IgG4 mAb), 400 mg IV Q3W |
| Study Phase | Phase 3 — Pivotal, Registration-Enabling |
| Target Enrollment | 500 patients (planned; 480 powered) |
| Target Sites | 200 sites across 20 countries |
| Document Version | 1.0 — FINAL |
| Effective Date | 16 March 2026 |
| Author | Clinical Operations, Oncobiologics Inc. |
| Status | APPROVED |

This document is CONFIDENTIAL and the property of Oncobiologics, Inc. Distribution is restricted to authorized personnel only.

# TABLE OF CONTENTS

1.  Executive Summary	3

2.  Study Overview & Protocol Synopsis	4

3.  Regulatory Strategy	5

4.  Competitive Landscape	8

5.  Country Selection Strategy	11

6.  Site Selection Strategy	14

7.  Enrollment Forecasting & Scenario Modeling	18

8.  Inclusion/Exclusion Criteria Design Rationale	22

9.  Vendor & Technology Strategy	25

10.  Risk Management Plan	27

11.  Budget & Resource Considerations	29

12.  Key Milestones & Timeline	31

Appendices.  Reference Tables & Tools	33

1. EXECUTIVE SUMMARY Strategic Overview for CERVIMAB-301 Clinical Operations

Purpose. This Clinical Operations Plan (COP) provides a comprehensive framework for the operational execution of CERVIMAB-301, a registration-enabling Phase 3 pivotal study of cervimab, an anti-PD-1 IgG4 monoclonal antibody, versus standard-of-care FOLFOX-4 + bevacizumab in patients with previously untreated dMMR/MSI-H metastatic colorectal cancer. The plan addresses all critical operational domains from country and site selection through enrollment completion and database lock.

Strategic Imperatives - Achieve 500-patient enrollment across 200 global sites within 24 months to support NDA/MAA submission - Ensure dMMR/MSI-H screening rates ≥70% via centralized molecular testing infrastructure - Execute flawlessly in a competitive landscape where pembrolizumab (KEYNOTE-177) and nivolumab (CheckMate 142) have established benchmarks - Maintain biomarker collection >95% compliance to enable exploratory TMB, PD-L1 subgroup analyses - Achieve zero critical inspection findings across US FDA, EMA, and PMDA regulatory interactions

## 1.1 Study at a Glance

| Primary Endpoint | PFS by BICR per RECIST v1.1 (HR=0.56 assumed; 90% power; 280 events) |
| --- | --- |
| Comparator | FOLFOX-4 + Bevacizumab (SoC for first-line dMMR/MSI-H mCRC) |
| Randomization | 1:1 stratified by ECOG PS, Region, RAS/BRAF status via IWRS |
| Enrollment Target | 500 patients (10% buffer over 480 powered) |
| Enrollment Period | 24 months (FPI to LPI target) |
| Sites | 200 sites ¦ 20 countries ¦ 5 regions |
| Enrollment Rate | ~20–22 patients/month peak; 2.5 pts/site/year average |
| Total Study Duration | ~48 months (24 enrollment + 24 minimum follow-up) |
| Estimated NDA Submission | Q4 2030 |

2. STUDY OVERVIEW & PROTOCOL SYNOPSIS CERVIMAB-301 Protocol Context

## 2.1 Disease Context & Unmet Need

Colorectal cancer (CRC) ranks as the third most diagnosed malignancy worldwide with an estimated 1.9 million new cases annually (GLOBOCAN 2022). Approximately 4–5% of metastatic CRC tumors exhibit dMMR/MSI-H status — a hypermutated phenotype uniquely sensitive to immune checkpoint blockade due to high neoantigen burden, dense TIL infiltration, and upregulated PD-L1/PD-L2 expression. Despite the approval of pembrolizumab (KEYNOTE-177, 2021) and nivolumab ± ipilimumab (CheckMate 142), cervimab's differentiated IgG4 backbone, sub-nanomolar PD-1 affinity (KD ~0.3 nM), and Phase 1/2 ORR of 45% at the 400 mg Q3W flat dose position it as a competitive entrant in this market.

## 2.2 Protocol Synopsis Summary

| Study Design | Phase 3, Randomized, Double-Blind, Double-Dummy, Placebo-Controlled, Multicenter International |
| --- | --- |
| Arms | Arm A: Cervimab 400 mg IV Q3W + FOLFOX-4 placebo Arm B: FOLFOX-4 + Bevacizumab + Cervimab placebo |
| Stratification | ECOG PS (0 vs 1) ¦ Region (NA/WE vs RoW) ¦ RAS/BRAF (WT vs Mutant) |
| Sample Size | 480 powered; 500 targeted (10% operational buffer) |
| Primary Endpoint | PFS by BICR per RECIST v1.1 |
| Key Secondary | OS, ORR, DoR, DCR@24 weeks, HRQoL (EORTC QLQ-C30, EQ-5D-5L) |
| Exploratory | TMB, PD-L1 TPS/CPS subgroups, PK, ADA, KRAS/NRAS/BRAF subgroups |
| Interim Analyses | IA1 @ 50% PFS events (futility+efficacy); IA2 @ 75% PFS events (efficacy) |
| DSMB | Independent board; charter-governed; unblinded safety review |
| Duration | Enrollment ~24 mo; Follow-up ≥24 mo; Total ~48 mo |

3. REGULATORY STRATEGY Global Regulatory Pathway — US FDA, EU EMA, APAC PMDA/NMPA

## 3.1 Strategic Regulatory Framework

CERVIMAB-301 is designed as a pivotal, registration-enabling study to support simultaneous NDA (US FDA), MAA (EU EMA), and J-NDA/BLA (PMDA/NMPA) submissions. The regulatory strategy capitalizes on available Breakthrough Therapy Designation (BTD) pathways in the US and PRIME eligibility in the EU, given the unmet need and early clinical evidence of substantial improvement over standard of care.

## 3.2 US FDA Strategy

US FDA Regulatory Pathway - IND submission under 21 CFR Part 312 — Active IND [IND-XXXXX]; annual progress reports required - Breakthrough Therapy Designation (BTD): Eligible per 21 CFR 312.82; compelling Phase 1/2 ORR=45% vs ~30% for SoC provides basis; BTD enables intensive FDA guidance and rolling review - Pre-NDA Meeting (Type B): Target scheduling 12–18 months prior to NDA submission to align on dataset package, labeling claims, and REMS considerations - NDA Pathway: 21 CFR Part 314 (Subpart H accelerated approval possible based on ORR if PFS interim is compelling; standard approval sought on PFS/OS) - Priority Review Voucher (PRV): Not applicable (CRC not orphan/rare pediatric), standard Priority Review expected based on BTD - FDA Guidance references: Guidance on Immune Checkpoint Inhibitors (2022); Clinical Trial Endpoints for Cancer Drug Approval (2018) - REMS Assessment: Immune-mediated AE profile warrants early FDA engagement; likely REMS-free given manageable irAE profile but formal assessment required

## 3.3 EU EMA Strategy

EU EMA Regulatory Pathway - EudraCT Number: [XXXX-XXXXXX-XX] registered; CT Application submitted per EU CTR (Regulation EU 536/2014) - PRIME Designation: Eligible given unmet need in dMMR/MSI-H mCRC; apply following Phase 2 data package submission; PRIME provides EMA rapporteur engagement and accelerated assessment - Scientific Advice: Request EMA Scientific Advice early (pre-Phase 3 start) on primary endpoint, BICR requirements, and biomarker confirmation strategy - MAA submission: Centralized Procedure (Regulation EC 726/2004) — mandatory for oncology biologics; Article 8(3) full dossier - Conditional Marketing Authorization (CMA): Consider if IA2 data are compelling and PFS mature; allows approval pending OS confirmation - Pediatric Investigation Plan (PIP): EMA PIP waiver expected given adult mCRC indication; submit PIP/waiver request pre-NDA - GDPR Compliance: All EU site data flows must comply with GDPR (Regulation EU 2016/679); DPA agreements with all EU sites/vendors required

## 3.4 APAC Regulatory Strategy

| Region | APAC Regulatory Approach | Priority |
| --- | --- | --- |
| Japan (PMDA) | J-NDA pathway; Japan included in global registrational dataset; PMDA consultation meeting recommended; Japanese population subgroup (~15% of global enrollment target); bridging data via Japanese site enrollment | High Priority |
| China (NMPA) | Supplemental IND (sIND) for China-specific sites; NMPA guidance on overseas multi-regional clinical trial acceptance; Chinese ethnic subgroup data required; ~20% of enrollment from China sites recommended | High Priority |
| South Korea (MFDS) | MFDS accepts MRCT data with Korean subgroup; 3–5 Korean sites planned; Korean IND required | Medium Priority |
| Australia (TGA) | CTN scheme; expedited pathway; no separate regulatory submission; data feeds into global NDA/MAA package | Medium Priority |
| Taiwan (TFDA) | TFDA accepts multi-regional trial data; TFDA IND required; 2–3 sites planned | Low Priority |

## 3.5 Key Regulatory Meetings & Milestones

| Milestone | Description | Target Timing |
| --- | --- | --- |
| Pre-Study Start | EMA Scientific Advice; FDA Pre-Phase 3 meeting; PMDA consultation; NMPA sIND submission | Q2 2026 |
| Study Initiation | IND amendments for all protocol versions; EudraCT registration; CTR submission | Q3 2026 |
| During Study | Annual IND reports; DSMB charter FDA submission; Safety aggregate reports | Ongoing |
| IA1 (~50% events) | Potential Conditional MA discussion with EMA if data compelling; BTD re-assessment | ~Q4 2027 |
| IA2 (~75% events) | Pre-NDA Type B meeting with FDA; PMDA pre-submission meeting; NMPA progress briefing | ~Q2 2028 |
| Primary Analysis | NDA submission (FDA); MAA submission (EMA); J-NDA/NMPA BLA submissions | Q4 2028–Q1 2029 |
| Post-Submission | FDA AdCom preparation; EMA CHMP Day 120/180 responses; label negotiations | 2029 |
| Approval Target | US FDA approval; EU EMA approval; PMDA approval | Q2–Q4 2030 |

## 3.6 IRB/IEC & Site Regulatory Coordination

Each site must obtain written IRB/IEC approval prior to initiation. Central IRB (US) and national ethics committee coordination (EU) should be pursued where regulations permit to accelerate approval timelines. Target: ≥80% of US sites on central IRB to reduce site startup time by 4–8 weeks per site.

4. COMPETITIVE LANDSCAPE PD-1/PD-L1 Inhibitors in dMMR/MSI-H mCRC — Approved & Emerging

## 4.1 Approved Competitor Landscape

The dMMR/MSI-H mCRC immune checkpoint space is increasingly crowded. Cervimab must differentiate on clinical outcomes, convenience (flat dosing, Q3W schedule), safety profile, and commercial positioning. Key approved competitors are detailed below:

| Agent | Sponsor | Target | Key Trial | Key Efficacy Data | Dose/Schedule | Approvals | Positioning |
| --- | --- | --- | --- | --- | --- | --- | --- |
| [object Object] | Merck & Co. | PD-1 (IgG4) | KEYNOTE-177 (Phase 3, 1L) | mPFS 16.5 mo vs 8.2 mo (HR=0.60) mOS NR vs 36.7 mo ORR 43.8% vs 33.1% | 200 mg Q3W or 400 mg Q6W | FDA 2021 EMA 2021 PMDA 2022 | Market leader; ~68% 1L share in dMMR mCRC; strong brand recognition |
| [object Object] | Bristol-Myers Squibb | PD-1 (IgG4) | CheckMate 142 (Phase 2, 2L+) | ORR 31.1% 12-mo OS 73% | 240 mg Q2W or 480 mg Q4W | FDA 2017 (2L+); no 1L approval in mCRC | 2L+ positioning; nivo+ipi combo in dMMR; no 1L approval yet |
| [object Object] | BMS | PD-1 + CTLA-4 | CheckMate 8HW (Phase 3, 1L) | mPFS 24.2 mo (nivo+ipi) vs 5.9 mo (chemo) HR=0.21 | Nivo 3mg/kg Q2W + Ipi 1mg/kg Q6W | FDA 2024 (1L dMMR/MSI-H) | New entrant; superior PFS data; increased irAE rate; concerns over combination tolerability |
| [object Object] | GSK/Tesaro | PD-1 (IgG4) | GARNET (Phase 1) | ORR 38.7% in dMMR solid tumors | 500 mg Q3W x4, then 1000 mg Q6W | FDA 2021 (pan- dMMR solid tumors) | Broad dMMR approval; no CRC-specific Phase 3; weaker CRC prescriber recognition |

## 4.2 Competitive Clinical Trials in Active Development

| Agent | Target | Trial | Phase | Status | Operational Note |
| --- | --- | --- | --- | --- | --- |
| Tislelizumab (BeiGene) | PD-1 | RATIONALE-313 (1L mCRC) | Phase 3 | Active, recruiting | Asia-heavy enrollment; potential NMPA competitor |
| Sintilimab (Innovent/Lilly) | PD-1 | Phase 3 in dMMR mCRC | Phase 3 | Planned | China-focused; will compete for Chinese sites |
| AK105 (Akesobio) | PD-1 | Phase 2/3 combination | Phase 2/3 | Recruiting | Novel PD-1; combination with VEGF; limited global footprint |
| Retifanlimab (Incyte) | PD-1 | Phase 2 dMMR solid tumors | Phase 2 | Recruiting | Pan-tumor dMMR; direct dostarlimab competitor |
| Ipilimumab+nivo combos | CTLA-4+PD-1 | Multiple academic | Phase 2 | Various | Academic; high irAE rate limits commercial threat |

## 4.3 Cervimab Competitive Differentiation Strategy

Cervimab Differentiation vs Pembrolizumab (Lead Competitor) - Flat 400 mg Q3W dosing — identical frequency to pembro 200 mg Q3W; simpler than Q6W option; no weight-based calculation - Sub-nanomolar PD-1 affinity (KD ~0.3 nM vs pembro KD ~0.027 nM — monitor closely; Phase 3 must demonstrate non-inferior or superior clinical outcomes) - Phase 1/2 ORR 45% in dMMR/MSI-H mCRC (vs KEYNOTE-177 ORR 43.8%) — numerically equivalent; confidence intervals warrant Phase 3 confirmation - Target HR=0.56 for CERVIMAB-301 PFS (vs HR=0.60 in KEYNOTE-177) — marginally superior assumption; statistical modeling supports 90% power at 480 patients - IgG4 backbone — same as pembro/nivo; established safety class; reduces regulatory novelty risk - Commercial strategy: price competitiveness, biosimilar-resistant IP position, expanded biomarker-defined patient selection (TMB, CPS subgroups)

## 4.4 Site Competition Risk — Enrollment Impact

Multiple concurrent PD-1 trials targeting identical dMMR/MSI-H mCRC patients create significant site enrollment competition. Sites actively running KEYNOTE-177 follow-on studies, CheckMate 8HW extensions, or emerging Chinese PD-1 trials will face competing protocol obligations. Mitigation strategies:

- Select sites with documented dMMR/MSI-H screening capability AND not exclusively committed to competing protocols

- Offer competitive site payments, screen failure reimbursement (dMMR/MSI-H testing is costly), and central lab support

- Prioritize sites in geographies underserved by existing approved PD-1 therapies (Latin America, Eastern Europe, Southeast Asia)

- Fast-track site selection: targeting site activation within 6 months of protocol finalization

5. COUNTRY SELECTION STRATEGY 20-Country Portfolio ¦ 500-Patient Enrollment Target

## 5.1 Country Selection Framework & Scoring Criteria

Country selection for CERVIMAB-301 was conducted using a weighted multi-criteria scoring model evaluating regulatory speed, disease epidemiology, site infrastructure, competitive landscape, and strategic value. Countries were scored on a 0–10 scale across 7 weighted criteria:

| Selection Criterion (Weight) | Definition & Rationale |
| --- | --- |
| Regulatory Speed & Approval Timeline (20%) | Speed from submission to HA approval; IND/CTA requirements; central IRB availability |
| CRC Incidence & dMMR/MSI-H Prevalence (20%) | National CRC burden; availability of MSI-H testing in local pathology ecosystem |
| Site Infrastructure & GCP Compliance (20%) | Academic cancer centers; phase 3 experience; ICH-GCP adherence; data quality history |
| Enrollment Velocity (15%) | Historical screen-to-randomize ratios; mCRC patient flow; treatment-naive pool |
| PD-1 Inhibitor Landscape Competition (10%) | Pembrolizumab/nivolumab commercial availability; competing trial burden |
| Regulatory/Commercial Strategic Value (10%) | Need for local data for approval (PMDA, NMPA); commercial market size |
| Operational Feasibility (5%) | Local CRO infrastructure; language/translation; logistics for IMP distribution |

## 5.2 Selected Country Portfolio — Target 20 Countries, 200 Sites, 500 Patients

| Country | Region | Sites (#) | Pts Target | Score (0–10) | SIV Target | Rationale |
| --- | --- | --- | --- | --- | --- | --- |
| United States | North America | 28 | 56 | 8 | SIV Q3 2026 | Central IRB; highest enrollment rate; BTD fast-start priority |
| Canada | North America | 8 | 16 | 8 | SIV Q3 2026 | Strong GCP; high dMMR testing rates; NCI-affiliated centers |
| Germany | Western Europe | 16 | 32 | 8 | SIV Q4 2026 | Fast CA approval; strong oncology infrastructure; ESMO sites |
| France | Western Europe | 12 | 24 | 8 | SIV Q4 2026 | FFCD network; excellent mCRC expertise; expedited ethics process |
| Spain | Western Europe | 10 | 20 | 8 | SIV Q4 2026 | TTCC network; high-volume oncology centers; fast CA |
| Italy | Western Europe | 10 | 20 | 7 | SIV Q4 2026 | GOIM/AIOM network; GCP-compliant; competitive enrollment |
| United Kingdom | Western Europe | 8 | 16 | 9 | SIV Q4 2026 | MHRA fast approval; NIHR/CRN network; centralized NHS oncology |
| Netherlands | Western Europe | 6 | 12 | 9 | SIV Q4 2026 | Academic excellence; Hartwig WGS infrastructure; high MSI testing |
| Poland | Eastern Europe | 12 | 24 | 8 | SIV Q1 2027 | Fast approval; lower competition; cost-effective sites; high volume |
| Czech Republic | Eastern Europe | 8 | 16 | 8 | SIV Q1 2027 | SUKL rapid approval; academic-community mix; cost-effective |
| Hungary | Eastern Europe | 6 | 12 | 7 | SIV Q1 2027 | OGYEI approval ~3 months; experienced GCP sites |
| Japan | Asia-Pacific | 20 | 40 | 8 | SIV Q2 2027 | PMDA bridging data required; 8 JCOG-affiliated sites; mandatory subgroup |
| China | Asia-Pacific | 25 | 50 | 7 | SIV Q2 2027 | NMPA sIND; high CRC burden; top 5 CRC tertiary hospitals targeted |
| South Korea | Asia-Pacific | 10 | 20 | 8 | SIV Q2 2027 | MFDS approval ~4 months; KCSG network; high-volume sites |
| Australia | Asia-Pacific | 8 | 16 | 9 | SIV Q2 2027 | TGA CTN ~4 weeks; AGITG network; English language |
| Brazil | Latin America | 12 | 24 | 7 | SIV Q2 2027 | ANVISA approval ~6 months; GBCARE network; high CRC volume |
| Argentina | Latin America | 8 | 16 | 7 | SIV Q2 2027 | ANMAT approval; GOCCHI network; cost-effective enrollment |
| Mexico | Latin America | 6 | 12 | 7 | SIV Q2 2027 | COFEPRIS improving; LACOG participating sites; growing GCP capacity |
| Israel | Middle East/Africa | 10 | 20 | 9 | SIV Q1 2027 | MOH fast approval; Sheba/Hadassah/Tel Aviv excellence; high MSI testing |
| Turkey | Middle East/Africa | 8 | 16 | 7 | SIV Q1 2027 | TITCK approval ~4 months; high mCRC volume; BEYKOZ/Marmara sites |

## 5.3 Regional Enrollment Allocation Summary

| Region | Sites | % Sites | Pts Target | % Patients | Strategic Rationale |
| --- | --- | --- | --- | --- | --- |
| North America | 36 | 18% | 72 | 14.4% | Highest enrollment rate; fast site activation; BTD benefit |
| Western Europe | 62 | 31% | 124 | 24.8% | Strong GCP; ESMO/KSMO networks; EMA MAA population |
| Eastern Europe | 26 | 13% | 52 | 10.4% | Cost-efficient; fast HA approval; competitive enrollment rates |
| Asia-Pacific | 63 | 31.5% | 126 | 25.2% | PMDA/NMPA bridging; largest CRC burden globally |
| Latin America | 26 | 13% | 52 | 10.4% | Growing GCP capacity; underserved by approved PD-1s |
| Middle East/Africa | 18 | 9% | 74 | 14.8% | Israel: best-in-class sites; Turkey: volume opportunity |
| [object Object] | [object Object] | [object Object] | [object Object] | [object Object] |  |

## 5.4 Country Risk Assessment

| Country/Region | Key Risk | Mitigation Strategy |
| --- | --- | --- |
| China | NMPA regulatory uncertainty; site GCP compliance variability; data integrity risk | Dual monitoring strategy; independent data audits; limit to top-tier Tier 1 hospitals; NMPA pre-submission consultation |
| Brazil | ANVISA approval delays (6–12 months); import license complexity for IMP | Early ANVISA submission; 12-month lead time; partner with established local CRO; IMP import buffer stock |
| Turkey | IRB process variability; political/currency risk | Central IRB use where available; financial risk hedge in contracts; maintain backup sites |
| Japan | PMDA regulatory requirements for Japanese subgroup; enrollment competition from local studies | Dedicated Japan CRA team; engage JCOG early; PMDA Type C meeting pre-study |
| All EU sites | EU CTR full implementation; GDPR data transfer complexity | CTIS submission; DPA templates; pre-validated CTIS workflow |

6. SITE SELECTION STRATEGY 200 Sites ¦ Qualification, Activation & Tiering

## 6.1 Site Selection Process Overview

Site selection for CERVIMAB-301 will follow a structured 5-phase process from feasibility to final selection, with continuous monitoring of activation readiness. The target is 200 activated sites within 6 months of protocol finalization (SIV Q3–Q4 2026 for Priority Tier 1 sites, phased activation through Q2 2027 for remaining countries).

| Phase | Activity | Timing | Description | Deliverable |
| --- | --- | --- | --- | --- |
| Phase 1 | Landscape & Feasibility Survey | Months 1–2 | Distribute site feasibility questionnaire to ~400 potential sites across 20 countries; assess dMMR/MSI-H testing capability, mCRC patient volume, competing protocols, PI availability | 400 sites approached |
| Phase 2 | Site Evaluation & Scoring | Months 2–3 | Site qualification visits (in-person or virtual) at top 300 sites; complete Site Qualification Checklist; GCP audit review; regulatory history review | 300 site visits |
| Phase 3 | Site Tiering & Final Selection | Month 3 | Score all evaluated sites; apply Tier 1/2/3 classification; select 200 sites; 50 backup sites identified | 200 selected + 50 backup |
| Phase 4 | Contract & IRB Initiation | Months 3–5 | Site CTAs/agreements; IRB/IEC submissions (central IRB US; local ethics EU/APAC); IMP import applications | CTA executed |
| Phase 5 | Site Initiation & Activation | Months 4–6 | Site Initiation Visits (SIVs) at all 200 sites; IWRS training; EDC system certification; local lab certification | 200 sites activated |

## 6.2 Site Qualification Criteria — Minimum Requirements

Mandatory Site Qualification Requirements (ALL must be met) - Minimum 15 new mCRC patients/year treated at site (documented from records) - On-site or contracted dMMR/MSI-H testing capability (IHC + PCR; or agreement with central lab turnaround ≤10 business days) - Phase 2/3 oncology trial experience within past 3 years; GCP-compliant facilities - Dedicated sub-investigator and study coordinator for CERVIMAB-301 - CT/MRI imaging capability with DICOM transmission for central BICR review - Infusion center capability: IV infusion administration, 30-minute infusion monitoring, irAE management protocols - ICH E6(R2) GCP training current (within 2 years) for all site staff - IWRS access and EDC system capability (Medidata Rave trained or willing to train) - Biobank/tissue storage capability: FFPE block archival storage; biospecimen handling per protocol

## 6.3 Site Scoring Model (0–100 Points)

| Scoring Criterion | Scoring Bands |
| --- | --- |
| mCRC Patient Volume (0–25 pts) | <15 pts/yr=0; 15–29=10; 30–49=18; ≥50=25 |
| MSI-H Testing Capability (0–20 pts) | No capability=0; Ref lab only (>10d)=8; On-site or ref lab ≤5d=20 |
| Phase 3 Trial Experience (0–15 pts) | None=0; Phase 2=8; Phase 3 oncology=15 |
| PI Experience with PD-1 Inhibitors (0–15 pts) | None=0; Phase 2=8; Phase 3 PD-1=15 |
| Site Regulatory/GCP Record (0–10 pts) | FDA 483/EMA findings in 3 yrs: -5 each; Clean record=10 |
| Data Quality & Timeliness (0–10 pts) | Based on sponsor audit or RACT data; >15% query rate=0 |
| Competing Protocol Commitment (0–5 pts) | ≥3 competing CKI trials=-5; 1–2=-2; 0=5 |

## 6.4 Site Tiering & Activation Strategy

| [object Object] | 60 sites (30% of total) | Top-quartile academic/comprehensive cancer centers; >50 mCRC pts/yr; in-house MSI-H; phase 3 PD-1 experience; FDA-cleared; target 4–5 patients/site/year → Activate FIRST (SIV within 4 months of protocol) |
| --- | --- | --- |
| [object Object] | 100 sites (50% of total) | Community oncology centers with strong mCRC volume and GCP record; 15–49 mCRC pts/yr; contracted MSI-H testing; ≥1 Phase 2/3 oncology study; target 2–3 patients/site/year → Activate 1–2 months after Tier 1 |
| [object Object] | 40 sites (20% of total) | Community sites or emerging-market sites with volume potential; may require more intensive monitoring; target 1–2 patients/site/year; useful for geographic coverage and RoW enrollment → Activate 2–3 months after Tier 2; contingent on Tier 1/2 performance |

## 6.5 Site Activation Timeline Targets

| Milestone | Target Date |
| --- | --- |
| First Site Activation (Tier 1 US/CA) | Month 4 post-protocol finalization (Q3 2026) |
| Tier 1 Sites Fully Activated (60 sites) | Month 6 (Q4 2026) |
| Tier 2 North America/Europe Activated | Month 8 (Q1 2027) |
| All Tier 2 Sites Activated (160 sites) | Month 10 (Q1 2027) |
| Tier 3 Sites Activated (200 sites) | Month 12 (Q2 2027) |
| First Patient In (FPI) — Target | Month 5 (Q4 2026) [Tier 1 US site] |
| All Sites Activated & Enrolling | Month 12 (Q2 2027) |
| Last Patient In (LPI) — Target | Month 29 (Q2 2029 from protocol finalization) |

7. ENROLLMENT FORECASTING & SCENARIO MODELING 500-Patient Target ¦ Monthly Projections ¦ Risk Scenarios

## 7.1 Enrollment Assumptions & Key Drivers

| Key Assumption | Value |
| --- | --- |
| dMMR/MSI-H Prevalence in mCRC | 4–5% of all metastatic CRC patients (epidemiologically) |
| MSI-H Screening Rate (site-level) | ~70% of eligible mCRC patients screened for MSI-H status |
| Screen-to-Randomize Conversion | ~35% of screened dMMR/MSI-H patients meet all I/E criteria and consent |
| Overall Screening Yield | ~70% x 35% = ~25% net randomization rate from eligible mCRC patients screened |
| Screen Failure Rate | Anticipated 65%; primary reasons: MSS/pMMR status (30%), prior systemic mCRC therapy (20%), organ function (10%), other (15%) |
| Average Site Enrollment Rate | ~2.5 patients/site/year (blended Tier 1/2/3); peak ~4.0 pts/site/yr for Tier 1 |
| Ramp-Up Period | Months 1–6 post-FPI: gradual ramp from 5 → 20 pts/month |
| Peak Enrollment Rate | Months 7–24: ~20–22 patients/month (all 200 sites enrolling) |
| Drop-Off Period | Months 21–24: enrollment taper as LPI approaches |
| Dropout/Withdrawal Rate | ~5% pre-randomization; ~8% during treatment (non-completion of randomized period) |

## 7.2 Monthly Enrollment Projection — Base Case

| Period | Sites Status | Rate (pts/month) | Cumulative Total | Phase |
| --- | --- | --- | --- | --- |
| Months 1–3 | Tier 1 sites activating; 10–15 sites open | 3–5 pts/month | 5–15 | Ramp-up phase |
| Months 4–6 | Tier 1 fully active; Tier 2 activating; ~80 sites | 8–12 pts/month | 16–51 | Accelerating |
| Months 7–12 | Tier 1+2 fully enrolling; ~160 sites | 15–20 pts/month | 52–171 | Full speed |
| Months 13–18 | All 200 sites enrolling | 20–22 pts/month | 172–302 | Peak enrollment |
| Months 19–24 | Target close to achieved; selective site pause | 15–20 pts/month | 303–420 | Maintaining pace |
| Months 25–29 | Buffer period for screen failures; LPI cleanup | 5–15 pts/month | 421–500 | Completion |
| [object Object] |  |  | bold(500) | Target enrollment |

## 7.3 Enrollment Scenario Analysis

Three enrollment scenarios were modeled to bracket operational uncertainty. The base case supports LPI within 29 months; optimistic case achieves LPI in 22 months; pessimistic case requires contingency actions (see Section 10) to recover to 32 months.

| Scenario | Assumptions | Months to LPI | LPI Target | Contingency Action |
| --- | --- | --- | --- | --- |
| [object Object] | Site activation 1 month early; screen-to-randomize 40%; 22 pts/month peak; dMMR testing <7 days | ~22 months | ~Q2 2028 | No contingency required; potential cost savings |
| [object Object] | Per projections above; 35% screen-to-randomize; 20 pts/month peak; all 200 sites reach enrollment | ~29 months | ~Q4 2028 | Standard monitoring; mid-study enrollment review |
| [object Object] | Site activation delays 2–3 months; screen failure rate >70%; only 160 sites effectively enrolling; 15 pts/month peak | ~36–40 months | ~Q4 2029 | Activate 20 backup sites; expand to 2 additional countries; increase screen failure support; consider protocol screen window extension |

## 7.4 dMMR/MSI-H Screening & Screen Failure Management

The key enrollment bottleneck in dMMR/MSI-H studies is molecular confirmation of tumor MSI status. To address this:

- Central laboratory partnership (Foundation Medicine, NovaBay, or equivalent) will provide IHC + PCR-based dMMR/MSI-H confirmation within 7 business days of tissue receipt

- Reflex testing protocol: all consenting mCRC patients at sites will undergo upfront MSI-H reflex testing from tumor tissue obtained at standard-of-care procedures — minimizing dedicated screening burden

- Local lab pathway: Sites with validated local MSI-H testing (IHC panel: MLH1, MSH2, MSH6, PMS2) may use local testing with central lab confirmation of equivocal results

- Screen failure cost subsidy: Sponsor will reimburse sites for dMMR/MSI-H testing costs for screen failures — a key site incentive given ~$800–1,200 per test cost

- Screen failure log: All screen failures tracked by reason; rolling analysis to optimize I/E criteria and site coaching

## 7.5 Site-Level Enrollment Tracking & Performance Management

An enrollment performance dashboard will be maintained in real-time via the EDC system and sponsor operational platform (Veeva Vault/Medidata integration). Monthly enrollment reviews will be held with all CRAs and site-level targets established:

- Green flag: Site enrolling ≥80% of target rate → routine monitoring

- Yellow flag: Site enrolling 50–79% of target rate → biweekly CRA check-in; root cause analysis

- Red flag: Site enrolling <50% of target rate for 2 consecutive months → site review board; potential Tier re-classification; possible replacement with backup site

8. INCLUSION/EXCLUSION CRITERIA DESIGN RATIONALE Clinical & Operational Justification for Each Criterion

## 8.1 Inclusion Criteria — Design Rationale

The inclusion criteria are designed to enroll a population that maximizes the likelihood of demonstrating the primary endpoint (PFS superiority) while ensuring generalizability to the intended label population and operational feasibility across 20 countries. Each criterion is justified below:

| Inclusion Criterion | Rationale | Enrollment Impact | Operational Note |
| --- | --- | --- | --- |
| [object Object] | Aligns with adult oncology indication; no pediatric mCRC data for cervimab; consistent with KEYNOTE-177 eligibility; PIP waiver expected from EMA | Low | Standard adult oncology criterion |
| [object Object] | Central pathology confirmation not required but archival tissue mandatory; cytology-only acceptable to preserve enrollment (vs biopsy-only requirement); unresectable/metastatic ensures appropriate disease stage for 1L systemic therapy eligibility | Medium | Cytology acceptable to reduce screen failures; avoids unnecessary re-biopsy burden |
| [object Object] | Biomarker-selected population per KEYNOTE-177 design; central lab confirmation ensures consistent testing; IHC alone (loss of MLH1/MSH2/MSH6/PMS2) or PCR-based MSI acceptable to maximize inclusion; dual testing reduces false negatives by ~8–12% | HIGH — primary enrollment driver | Central lab mandatory to prevent site variability; 7-day turnaround target; screen failure cost reimbursement for MSS patients |
| [object Object] | 1L treatment-naive population consistent with KEYNOTE-177 and planned labeling; prior adjuvant therapy ≥6 months before randomization permitted — aligns with standard practice and KEYNOTE-177 eligibility; avoids penalizing patients for standard prior treatment | Medium | 6-month adjuvant washout is standard; operational guidance needed on documenting adjuvant completion date accurately |
| [object Object] | Required for PFS endpoint validity; 28-day window consistent with KEYNOTE-177; CT preferred; MRI where CT contraindicated; scans must be within 28 days of randomization (not screening) | Low-Medium | Operationally: sites must not delay randomization beyond 28 days from imaging; re-imaging required if window exceeded |
| [object Object] | Functional status threshold standard for PD-1 monotherapy trials; ECOG 2 excluded to ensure treatment-tolerability and endpoint interpretability; stratification factor | Low | Sites must use ECOG scale consistently; training provided at SIV; ECOG 2 most common soft ineligibility — do not waive |
| [object Object] | Standard thresholds; consistent with KEYNOTE-177 and nivolumab trials; Gilbert syndrome bilirubin exception (≤3x ULN) included to avoid exclusion of benign hyperbilirubinemia; hepatic met exception (ALT/AST ≤5x ULN) | Low | Lab thresholds must be confirmed within 7 days of randomization; hepatic met exception important — operationally verify liver disease documentation at screen |
| [object Object] | Standard reproductive safety; aligns with ICH E8, FDA and EMA reproductive toxicity guidance; serum hCG test within 72 hours of first dose; 6-month post-treatment contraception consistent with IgG4 elimination half-life | Low | Operationally burden at sites with high WOCBP enrollment; ensure site workflows for timely pre-dose serum hCG |
| [object Object] | ICH E6(R2), 21 CFR Part 50 requirement; patient autonomy; document before ANY screening procedure including MSI-H testing | None | ICH/GCP requirement; site must document consent date precedes all screening assessments |

## 8.2 Exclusion Criteria — Design Rationale

| Exclusion Criterion | Rationale | Screen Failure Risk | Operational Note |
| --- | --- | --- | --- |
| [object Object] | Prevents enrollment of patients pre-sensitized or refractory to checkpoint blockade; essential for 1L cervimab claim; primary competitive differentiation criterion | Low | Sites must check prior immunotherapy history thoroughly; note pembrolizumab use in Stage III adjuvant setting is increasing — document carefully |
| [object Object] | Immune activation risk from PD-1 blockade; irAE risk amplified in autoimmune patients; 2-year window standard for ICI trials; replacement therapy (thyroid, adrenal) permissible | Medium — can cause screen failures | Sites must document autoimmune history; replacement therapy ≠ active autoimmune disease; FAQ guidance for sites on what qualifies |
| [object Object] | Highest risk irAE for colitis with PD-1 inhibitor; ICI-mediated colitis can be severe/fatal in IBD patients; conservative exclusion consistent with all ICI labels and KEYNOTE-177 | Low | IBD must be actively queried; endoscopy results may be needed in ambiguous cases |
| [object Object] | Safety signal: prior severe irAE predicts recurrence; essential to protect patient safety | Low | Document grade and nature of prior irAE; lesser irAEs (Grade 1–2) permissible |
| [object Object] | Immunosuppression would blunt PD-1 blockade efficacy and mask irAE assessment; 14-day washout standard; inhaled/topical steroids and replacement doses permissible | Medium — common in cancer patients | Careful documentation of steroid dose and indication; replacement dose (≤10 mg) is not excluded; operationally require precise steroid documentation at screening |
| [object Object] | Untreated CNS mets: safety risk with corticosteroid interactions; treated/asymptomatic exception per standard oncology practice and KEYNOTE-177; reduces unnecessary exclusions | Low-Medium | Sites must document CNS imaging and treatment history; exception criteria require documentation of radiotherapy completion date and corticosteroid taper |
| [object Object] | Explicitly excludes patients whose tumor status would preclude PD-1 benefit; reinforces biomarker selection strategy | Low | Central lab confirmation serves as the primary gating step; local MSS result alone is insufficient to exclude — central confirmation required for all borderline cases |
| [object Object] | Severe irAE: PD-1 inhibitors associated with pneumonitis; baseline ILD dramatically elevates risk; consistent with all ICI labels | Low | Chest CT review required at screening; sites must query ILD history proactively |
| [object Object] | Immune compromise risk; HBV/HCV hepatitis flare risk with immunotherapy; stable well-controlled HIV (CD4 ≥350, no ART required) permissible — consistent with emerging inclusive criteria | Low | Sites in high-prevalence regions must routinely screen; viral load documentation required; stable HIV should NOT trigger exclusion per protocol |
| [object Object] | Wound healing risk (bevacizumab arm); procedural complications; 28-day window standard | Low | Minor procedures (biopsy, port placement) do NOT qualify as major surgery; sites need clarity on definition |
| [object Object] | Competing disease endpoint confounding; standard exclusion for oncology trials; exceptions for non-invasive skin cancers and carcinoma in situ are consistent with industry standard | Low | Prostate cancer on active surveillance, low-risk thyroid cancers need case-by-case medical monitor review |

## 8.3 Criteria Optimization — Operational Recommendations

I/E Criteria Design Improvements vs Standard ICI Template - ADDED cytology-acceptable CRC confirmation: reduces re-biopsy requirement; decreases screen failures ~8% - ADDED central lab dMMR/MSI-H confirmation with IHC OR PCR (not AND): accepts either modality; reduces false-negative exclusions by ~10%; increases eligible pool - ADDED Gilbert syndrome bilirubin exception: standard of care; prevents exclusion of ~3% of patients with benign hyperbilirubinemia - ADDED hepatic metastasis LFT exception: ≤5x ULN for AST/ALT; prevents exclusion of patients with liver mets (30–40% of mCRC population) - ADDED stable HIV exception: progressive inclusion; CD4 ≥350 and no ART-required HIV does not contraindicate cervimab; aligns with FDA recommendations - CONSIDERED but EXCLUDED: prior adjuvant oxaliplatin restriction — decided NOT to exclude; prior adjuvant chemo ≥6 months prior is permitted; inclusion of this population increases eligible pool by ~15% - CONSIDERED but EXCLUDED: TMB threshold inclusion criterion — decided against TMB cut-off; TMB is exploratory; imposing TMB threshold at screen would dramatically reduce eligible pool and introduce central lab delays

9. VENDOR & TECHNOLOGY STRATEGY Functional Service Providers & Clinical Technology Stack

## 9.1 Key Vendor Categories & Selection Rationale

| Vendor Category | Function & Model | Preferred Vendors | Key Requirement |
| --- | --- | --- | --- |
| [object Object] | Preferred model: Hybrid FSP with regional CRO partners for APAC/LATAM countries; global CRO for US/EU; sponsor-retained medical monitoring and biostatistics | ICON, Syneos Health, PRA Health Sciences; regional: Novatek (EE), Medpace (APAC) | RFP issued Q1 2026; selection by Q2 2026 |
| [object Object] | Central dMMR/MSI-H testing is mission-critical; one global central lab with regional depots; CLIA/CAP certified; ISO 15189; DICOM integration for NGS reports | Foundation Medicine, Labcorp Oncology, BioReference Oncology | Must demonstrate <7 business-day TAT; experience with IHC 4-plex + PCR MSI; validated NGS TMB panel |
| [object Object] | Blinded Independent Central Review for RECIST v1.1 PFS endpoint; mandatory for FDA/EMA registration; DICOM image transfer from all 200 sites | Medidata Rave Imaging, BioClinica/Certis, Imaging Endpoint | RFP Q1 2026; BICR SOP and charter pre-approved by FDA/EMA consultation |
| [object Object] | 1:1 randomization and stratification management; drug supply management; real-time enrollment tracking by stratum | Medidata Rave IRT, Veeva Vault IRT, Almac iRIS | Integration with EDC system critical; 24/7 support required; validated for GxP use |
| [object Object] | Electronic data capture; >500 eCRF pages expected; multi-language support; 21 CFR Part 11 compliant | Medidata Rave, Oracle InForm, Veeva Vault EDC | Preferred: Medidata Rave for FDA/EMA audit trail familiarity; integration with BICR/IWRS |
| [object Object] | SAE collection and expedited reporting; IND safety reports (7-day/15-day); aggregate DSUR; DSMB data package | Argus (Oracle); Veeva Vault Safety | PV agreements required before FPI; 24-hour SAE notification system |
| [object Object] | Cervimab PK sampling (pre/post-infusion at C1, C3, C6, C9); anti-drug antibody (ADA) analysis | Covance/Labcorp Bioanalytical; Pacific Bioanalytical; Charles River | Validated bioanalytical method (Gyrolab or MSD platform); bridged to Phase 1/2 PK assay |
| [object Object] | Independent charter-governed DSMB; unblinded statistical analysis at IA1/IA2; access to unblinded safety | Sponsor Statistical Group + independent statistician; DSMB charter to FDA | DSMB charter finalized before FPI; DSMB SOP for unblinding procedures |

10. RISK MANAGEMENT PLAN Proactive Risk Identification, Scoring & Mitigation

## 10.1 Risk Register

Risks are scored by Likelihood (1–5) x Impact (1–5) = Risk Score (1–25). Red ≥15, Yellow 8–14, Green <8.

| Risk ID | Risk Description | Consequence | Likelihood (1–5) | Impact (1–5) | Score | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| [object Object] | Low dMMR/MSI-H screen-to-randomize rate (<30%) | Screen failure burden exceeds budget; LPI delayed >6 months | 4 | 5 | [object Object] | Central lab with reflex testing; screen failure cost reimbursement; expanded site selection with high MSI-H testing rates |
| [object Object] | Competitive enrollment pressure from pembrolizumab commercial use | Sites fail to enroll in countries where pembro is SoC | 4 | 4 | [object Object] | Target geographies where pembro not reimbursed; emphasize 1L treatment-naive pool; investigator-blinded competitive analysis |
| [object Object] | Site activation delays in APAC/LATAM (NMPA, ANVISA) | Enrollment ramp delayed 3–6 months; LPI impact | 3 | 4 | [object Object] | Early HA engagement; 12-month NMPA/ANVISA lead time built into plan; backup sites in faster-approval countries |
| [object Object] | BICR/imaging data quality failures | RECIST v1.1 per-protocol set violations; FDA inspection risk | 2 | 5 | [object Object] | Central BICR with DICOM validation at SIV; site imaging quality check first 3 patients; investigator RECIST training module |
| [object Object] | High irAE rate leading to treatment discontinuations | Safety imbalance; impact on PFS endpoint; labeling risk | 3 | 4 | [object Object] | irAE management algorithm in protocol; real-time DSMB safety review; medical monitor 24-hour hotline for sites |
| [object Object] | Biomarker sample collection failure (<90% compliance) | Exploratory TMB/PD-L1 endpoints underpowered | 3 | 3 | [object Object] | Biomarker coordinator at Tier 1 sites; central lab tissue receipt confirmation loop; protocol requires archival tissue |
| [object Object] | Protocol amendment required (I/E modification) | 6–12 week delay for IRB re-submission; enrollment pause | 2 | 4 | [object Object] | Front-load I/E design review; medical monitor FAQ document; avoid amendments via thorough pre-launch testing |
| [object Object] | Data integrity concern at high-enrollment sites | GCP finding at inspection; potential data exclusion | 2 | 5 | [object Object] | Risk-based monitoring (RBM); central statistical monitoring (CSM); RBQM system (Medidata Risk) |

11. BUDGET & RESOURCE CONSIDERATIONS Order-of-Magnitude Estimates — Phase 3 dMMR/MSI-H mCRC Global Trial

## 11.1 Budget Framework

The following represents order-of-magnitude estimates for a 500-patient global Phase 3 oncology trial of this complexity. All figures are USD. Final budgets subject to CRO/vendor RFP and contract negotiation.

| Site Costs (per patient direct costs, labs, assessments) | ~$45,000–55,000/patient × 500 pts = $22.5–27.5M |
| --- | --- |
| Site Screen Failure Reimbursement | ~800 screen failures × $2,500 avg = ~$2.0M |
| Central BICR Imaging Review | ~500 pts × $8,000–12,000 avg = $4.0–6.0M |
| Central Laboratory (MSI-H, PK, ADA, TMB, PD-L1) | ~$3.5–5.0M (blended central lab costs) |
| CRO / FSP Operational (monitoring, data management, regulatory) | ~$18–25M (FSP hybrid model) |
| IWRS / IRT / EDC Platform | ~$2.0–3.5M |
| Pharmacovigilance & Safety | ~$1.5–2.5M |
| Statistical Analysis & Reporting | ~$2.0–4.0M |
| Regulatory Filing & Agency Fees (FDA, EMA, PMDA, NMPA) | ~$1.5–2.5M |
| IMP Manufacturing & Distribution (cervimab + placebo) | ~$15–20M (for 48-month trial) |
| Contingency (15%) | ~$10–14M |

Total Estimated Budget (Order of Magnitude)~$82–110M USD

## 11.2 Staffing (Sponsor-Side)

| Role | Headcount & Responsibility |
| --- | --- |
| Clinical Operations Lead (Global) | 1 FTE — overall COP execution, vendor oversight |
| Regional Clinical Operations Managers | 5 FTE — NA, WEU, EEU, APAC, LATAM/MEA |
| Clinical Research Associates (Sponsor CRAs) | 8 FTE oversight CRAs (FSP CRAs ~40–60 additional) |
| Medical Monitor | 2 FTE — 24/7 site medical support; SAE review |
| Biostatistician (Lead + DSMB statistician) | 2 FTE (1 internal, 1 independent for DSMB) |
| Data Management | 3 FTE — EDC build, SDTM/ADaM, database lock |
| Regulatory Affairs (Global) | 3 FTE — US NDA, EMA MAA, APAC submissions |
| Pharmacovigilance | 2 FTE — SAE management; IND reports; DSUR |
| Project Manager | 2 FTE — timeline, budget, risk tracking |

12. KEY MILESTONES & TIMELINE CERVIMAB-301 Master Study Timeline

## 12.1 Master Timeline

| Milestone Period | Key Activities & Events |
| --- | --- |
| Q2 2026 | Protocol Finalization v1.0; CRO Selection; FDA Pre-Phase 3 meeting; EMA Scientific Advice; NMPA sIND submission; Central lab & BICR vendor selection |
| Q3 2026 | IND amendments submitted; CTIS EU submission; Site feasibility surveys complete; Tier 1 site CTAs executed; US central IRB submission |
| Q4 2026 | Tier 1 sites activated (60 sites); FPI — First Patient In; Site Initiation Visits (Tier 1 complete); DSMB constituted; PV system go-live |
| Q1 2027 | Tier 2 sites activating; ~100 sites open; enrollment rate 10–15 pts/month; Japan/China site activations |
| Q2 2027 | All 200 sites activated; Enrollment rate target 20 pts/month; APAC/LATAM fully enrolled; Ongoing RBQM monitoring |
| Q4 2027 | IA1 (~50% PFS events, ~140 events); DSMB review; Enrollment ~300 patients; Potential BTD re-assessment/CMA EMA discussion |
| Q2 2028 | IA2 (~75% PFS events, ~210 events); Pre-NDA FDA Type B meeting; PMDA pre-submission meeting; Enrollment ~450 patients |
| Q4 2028 | LPI — Last Patient In (target ~500 patients); Enrollment complete; Begin minimum 24-month follow-up; Database monitoring intensified |
| Q4 2028–Q1 2029 | Primary Analysis (280 PFS events achieved); Database lock; Unblinding; CSR preparation |
| Q2–Q3 2029 | NDA submission to FDA; MAA submission to EMA; J-NDA submission to PMDA; NMPA BLA submission |
| 2029–2030 | FDA review; EMA CHMP assessment; PMDA review; FDA AdCom (anticipated); Label negotiation |
| Q2–Q4 2030 | US FDA Approval (target); EU EMA CHMP Positive Opinion; PMDA Approval; Commercial launch preparation |

Critical Path Items - Central dMMR/MSI-H lab setup and validation must complete 8 weeks before FPI — any delay directly impacts enrollment start - BICR vendor SOP and imaging charter must be FDA/EMA-reviewed before FPI — post-hoc BICR changes invalidate registration dataset - NMPA sIND and ANVISA approvals are on critical path for Asia and LATAM enrollment contributions — 12-month lead time required - DSMB charter must be finalized and submitted to FDA before IA1 — failure to do so risks FDA questioning of data integrity at NDA review - IA2 data package quality drives NDA submission readiness — pre-NDA Type B meeting must occur ≥6 months before submission

APPENDICES Supporting Reference Tables & Tools

## Appendix A: I/E Criteria Operational Quick Reference

The following summarizes key operational clarifications for I/E criteria implementation at site level:

| I/E Item | Operational Clarification |
| --- | --- |
| Prior adjuvant therapy | Permitted IF completed ≥6 months before randomization. Document adjuvant regimen end date precisely. FOLFOX adjuvant is permitted. |
| dMMR/MSI-H confirmation | IHC alone (loss of ≥1 MMR protein) OR PCR MSI-H alone sufficient. Central lab confirmation required. Local result may be used provisionally but central result is definitive. |
| Corticosteroid exclusion | Only SYSTEMIC steroids >10 mg prednisone/day. Inhaled, topical, physiologic replacement (e.g., 5–7.5 mg for adrenal insufficiency) are NOT excluded. Document dose, route, indication. |
| Active autoimmune disease | Replacement therapy (levothyroxine, insulin, steroids for adrenal) does NOT qualify as active autoimmune requiring systemic treatment. Rheumatoid arthritis on hydroxychloroquine alone — discuss with medical monitor. |
| Gilbert syndrome | Total bilirubin ≤3× ULN acceptable. Must have documented Gilbert diagnosis (UGT1A1 genotype or prior clinical diagnosis). |
| Stable HIV | CD4 ≥350 cells/µL AND not requiring ART = eligible. Document CD4 and ART status. HIV+ patients on ART = excluded. |
| Prior malignancy within 3 years | BCC, SCC of skin, CIS of any organ = not excluded. Low-risk localized prostate cancer (Gleason ≤6, surveillance) — discuss with medical monitor on case-by-case basis. |
| Treated CNS metastases | Patient eligible if: (a) treated by surgery/RT, (b) asymptomatic, (c) no corticosteroids required (or tapering, stable ≥4 weeks). Document RT completion date; last corticosteroid dose. |

## Appendix B: Country Regulatory Submission Summary

| Country | Agency | Submission Type | Regulation | HA Approval Timeline | Site Activation Lead | IRB/IEC Type | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| United States | FDA | IND Amendment | 21 CFR 312 | ~30 days (30-day review) | ~4 months (site level) | Central IRB available | BTD holder |
| Canada | Health Canada | CTA | Division 5 Regs | ~30 days | ~4 months | REB per site | No special designation |
| Germany | BfArM/PEI | CTA (CTIS) | EU CTR 536/2014 | ~45 days | ~5 months | Ethics committee | Strong GCP |
| France | ANSM | CTA (CTIS) | EU CTR 536/2014 | ~45 days | ~5 months | CPP (Central) | Fast ANSM |
| United Kingdom | MHRA | CTA (UKCA post-Brexit) | UK SI 536/2004 | ~30 days | ~4 months | NHS HRA approval | Fast MHRA |
| Japan | PMDA | J-IND (CTA) | Pharma Affairs Law | ~60 days | ~7 months | IRB per site | PMDA meeting req. |
| China | NMPA | sIND | Chinese GCP | ~60–90 days | ~9–12 months | Ethics committee | NMPA pre-consult req. |
| Brazil | ANVISA | CONEP/ANVISA | Res. RDC 204/2017 | ~90–180 days | ~12 months | CONEP + local | Early submission critical |
| Australia | TGA | CTN Scheme | TG Act 1989 | ~4 weeks | ~4 months | HREC per site | Fastest APAC |
| Israel | MOH | CTA | MOH Order 2017 | ~30–45 days | ~4 months | Helsinki comm. | Excellent sites |

## Appendix C: Screen Failure Tracking Categories

| Screen Failure Reason | Estimated Frequency |
| --- | --- |
| MSS/pMMR tumor status (local or central) | Anticipated ~30% of screen failures |
| Prior systemic therapy for metastatic CRC | Anticipated ~20% of screen failures |
| ECOG PS ≥2 | Anticipated ~10% of screen failures |
| Inadequate organ function | Anticipated ~10% of screen failures |
| Active autoimmune disease / prohibited medications | Anticipated ~8% of screen failures |
| Patient withdrawal of consent | Anticipated ~5% of screen failures |
| No measurable lesion per RECIST v1.1 | Anticipated ~5% of screen failures |
| Other / multiple reasons | Anticipated ~12% of screen failures |

## Appendix D: Enrollment Model Summary — Base Case Monthly Table

| Month | Status | Open Sites | New Screen | Randomized (Month) | Cumulative Enrolled | Remaining |
| --- | --- | --- | --- | --- | --- | --- |
| Month 1 | Tier 1 activating | 5 | 2 | 0 | 2 | 498 |
| Month 2 | Tier 1 sites open | 10 | 5 | 2 | 7 | 493 |
| Month 3 | Tier 1 fully active | 20 | 8 | 5 | 12 | 488 |
| Month 4 | Tier 2 US/EU activating | 35 | 12 | 7 | 19 | 481 |
| Month 5 | Tier 2 expanding; FPI Month 5 | 55 | 14 | 9 | 28 | 472 |
| Month 6 | ~80 sites active | 80 | 16 | 11 | 39 | 461 |
| Month 8 | ~120 sites active | 120 | 19 | 14 | 53 | 447 |
| Month 10 | ~160 sites active | 160 | 21 | 16 | 69 | 431 |
| Month 12 | 200 sites active | 200 | 22 | 18 | 87 | 413 |
| Month 15 | Peak enrollment | 200 | 22 | 20 | 127 | 373 |
| Month 18 | Continued peak | 200 | 21 | 20 | 187 | 313 |
| Month 21 | Approaching target | 200 | 18 | 18 | 241 | 259 |
| Month 24 | End of primary enrollment window | 200 | 15 | 15 | 286 | 214 |
| Month 27 | Buffer enrollment | 200 | 10 | 12 | 322 | 178 |
| Month 29 | LPI target — 500 enrolled | 200 | 5 | 8 | 500 | 0 |

END OF CLINICAL OPERATIONS PLAN — CERVIMAB-301 v1.0

This document is the property of Oncobiologics, Inc. and is intended solely for authorized recipients. Unauthorized distribution is prohibited. © 2026 Oncobiologics, Inc.